## Cost Estimates
Item_ID | Name | Category | Optimistic | Most Likely | Pessimistic | Distribution
C001 | Engineering Labor | Labor | 150 | 180 | 220 | Triangular
C002 | Materials - Steel | Materials | 80 | 100 | 130 | Triangular
C003 | Materials - Electrical | Materials | 45 | 55 | 70 | PERT
C004 | Equipment Rental | Equipment | 30 | 40 | 55 | Triangular
C005 | Subcontractor - HVAC | Subcontractor | 120 | 150 | 190 | PERT
C006 | Permits & Fees | Admin | 15 | 20 | 30 | Triangular
C007 | Project Management | Labor | 60 | 75 | 95 | Triangular
C008 | Contingency Reserve | Contingency | 0 | 50 | 100 | Triangular

## Cost Risks
Risk_ID | Description | Item_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
CR001 | Steel price increase | C002 | 0.4 | 10 | 20 | 35 | Triangular | Open
CR002 | Labor shortage premium | C001,C007 | 0.25 | 15 | 30 | 50 | PERT | Open
CR003 | Permit delays - expedite fees | C006 | 0.15 | 5 | 10 | 18 | Triangular | Open
CR004 | Equipment breakdown | C004 | 0.2 | 8 | 15 | 30 | Triangular | Open
CR005 | Scope change - additional electrical | C003 | 0.3 | 12 | 25 | 45 | PERT | Open

## Instructions
COST RISK ANALYZER - TEMPLATE INSTRUCTIONS
COST ESTIMATES SHEET
Item_ID | Unique identifier for each cost item (e.g., C001, COST-001)
Name | Cost item name or description
Category | Cost category for grouping (e.g., Labor, Materials, Equipment)
Optimistic | Best-case cost (if everything goes well)
Most Likely | Most likely/expected cost (typical scenario)
Pessimistic | Worst-case cost (if things go wrong)
Distribution | Triangular (default) or PERT
COST RISKS SHEET (Optional)
Risk_ID | Unique identifier for each risk
Description | Description of the risk event
Item_ID | Cost item(s) affected by this risk (comma-separated for multiple)
Probability | Likelihood of risk occurring (0 to 1, e.g., 0.3 = 30%)
Optimistic | Minimum additional cost if risk occurs
Most Likely | Expected additional cost if risk occurs
Pessimistic | Maximum additional cost if risk occurs
Distribution | Triangular (default) or PERT
Status | Open or Closed (only Open risks are included in analysis)
TIPS
• Optimistic should be ≤ Most Likely ≤ Pessimistic
• Use consistent currency units (e.g., all in $K or all in $)
• Use PERT distribution when you want the most likely value to have more weight
• Categories help group costs for breakdown analysis
• Delete sample data and add your own before uploading