## Schedule
Task_ID | Name | Start Date | End Date | Optimistic | Most Likely | Pessimistic | Predecessors | Distribution
T001 | Project Initiation | 2025-03-01 | 2025-03-11 | 8 | 10 | 15 |  | Triangular
T002 | Requirements Gathering | 2025-03-11 | 2025-03-26 | 12 | 15 | 22 | T001 | PERT
T003 | Design Phase | 2025-03-26 | 2025-04-15 | 15 | 20 | 30 | T002 | Triangular
T004 | Development - Module A | 2025-04-15 | 2025-05-15 | 25 | 30 | 42 | T003 | PERT
T005 | Development - Module B | 2025-04-15 | 2025-05-10 | 20 | 25 | 35 | T003 | Triangular
T006 | Integration Testing | 2025-05-15 | 2025-05-30 | 12 | 15 | 22 | T004,T005 | PERT
T007 | User Acceptance Testing | 2025-05-30 | 2025-06-14 | 12 | 15 | 20 | T006 | Triangular
T008 | Deployment | 2025-06-14 | 2025-06-24 | 8 | 10 | 15 | T007 | Triangular

## Cost Estimates
Item_ID | Name | Category | Task_ID | Cost_Type | Optimistic | Most Likely | Pessimistic | Distribution
C001 | Project Management | Labor | T001,T002,T003 | Variable | 40 | 50 | 70 | Triangular
C002 | Business Analyst | Labor | T002 | Variable | 25 | 30 | 40 | PERT
C003 | Solution Architect | Labor | T003 | Variable | 35 | 45 | 60 | Triangular
C004 | Development Team | Labor | T004,T005 | Variable | 120 | 150 | 200 | PERT
C005 | QA Team | Labor | T006,T007 | Variable | 45 | 55 | 75 | Triangular
C006 | Infrastructure | Equipment |  | Fixed | 30 | 40 | 55 | Triangular
C007 | Software Licenses | Software |  | Fixed | 20 | 25 | 35 | Triangular
C008 | Training | Services | T008 | Fixed | 15 | 20 | 30 | PERT

## Schedule Risks
Risk_ID | Description | Task_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
SR001 | Requirements change mid-project | T002,T003 | 0.3 | 5 | 10 | 18 | Triangular | Open
SR002 | Key resource unavailable | T004 | 0.2 | 7 | 12 | 20 | PERT | Open
SR003 | Integration complexity higher than expected | T006 | 0.35 | 5 | 8 | 15 | Triangular | Open
SR004 | UAT feedback requires rework | T007 | 0.25 | 3 | 7 | 14 | Triangular | Open

## Cost Risks
Risk_ID | Description | Item_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
CR001 | Developer rate increase | C004 | 0.25 | 15 | 25 | 40 | Triangular | Open
CR002 | Additional infrastructure needed | C006 | 0.2 | 10 | 20 | 35 | PERT | Open
CR003 | Extended testing required | C005 | 0.3 | 12 | 20 | 32 | Triangular | Open
CR004 | Scope creep - new features | C001,C004 | 0.35 | 20 | 35 | 55 | PERT | Open

## Instructions
INTEGRATED PROJECT RISK ANALYZER - TEMPLATE
This template contains 4 data sheets:
1. Schedule - Project tasks with durations
2. Cost Estimates - Cost items linked to tasks
3. Schedule Risks - Discrete schedule risk events
4. Cost Risks - Discrete cost risk events
SCHEDULE SHEET
Task_ID | Unique task identifier (e.g., T001)
Name | Task description
Start Date / End Date | Planned dates
Optimistic | Best-case duration (days)
Most Likely | Expected duration (days)
Pessimistic | Worst-case duration (days)
Predecessors | Comma-separated Task_IDs
Distribution | Triangular (default) or PERT
COST ESTIMATES SHEET
Item_ID | Unique cost item identifier (e.g., C001)
Name | Cost item description
Category | Cost category for grouping
Task_ID | Linked task(s) - comma-separated for multiple
Cost_Type | Fixed or Variable (Variable scales with task duration)
Optimistic/ML/Pessimistic | Cost estimates
Distribution | Triangular (default) or PERT
SCHEDULE RISKS / COST RISKS SHEETS
Risk_ID | Unique risk identifier
Description | Risk event description
Task_ID / Item_ID | Affected tasks or cost items
Probability | 0-1 (e.g., 0.30 = 30%)
Optimistic/ML/Pessimistic | Impact if risk occurs
Status | Open or Closed
TIPS
• Variable costs scale with task duration changes
• Link costs to tasks for cash flow analysis
• Use consistent IDs between sheets
• Delete sample data before uploading