## Cost Estimates
Item_ID | Name | Category | Optimistic | Most Likely | Pessimistic | Distribution
C001 | Project Management | Labor | 40000 | 50000 | 68000 | Triangular
C002 | Development Team | Labor | 120000 | 150000 | 195000 | PERT
C003 | Software Licenses | Software | 25000 | 30000 | 38000 | Triangular
C004 | Infrastructure | Hardware | 45000 | 55000 | 72000 | Triangular
C005 | Training & Documentation | Services | 15000 | 20000 | 28000 | PERT

## Cost Risks
Risk_ID | Description | Item_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
CR001 | Scope changes | C001,C002 | 0.3 | 15000 | 30000 | 50000 | Triangular | Open
CR002 | License cost increase | C003 | 0.2 | 5000 | 10000 | 18000 | Triangular | Open
CR003 | Additional infrastructure needs | C004 | 0.25 | 10000 | 20000 | 35000 | PERT | Open

## Vendor Info
VENDOR INFORMATION
Company Name: | [Enter your company name]
Contact Person: | [Enter contact name]
Email: | [Enter email]
Phone: | [Enter phone]
Date Submitted: | [Enter date]
PROPOSAL NOTES
[Add any notes or assumptions about your schedule estimates]

## Instructions
RFP COST TEMPLATE - VENDOR INSTRUCTIONS
Thank you for your proposal. Please complete this template to help us
evaluate cost risk across all vendors consistently.
HOW TO COMPLETE
COST ITEMS SHEET:
1. Item_ID | Unique ID for each cost item (e.g., C001)
2. Description | Brief description of the cost item
3. Category | Cost category (Labor, Software, Hardware, Services, etc.)
4. Optimistic | Best-case cost if everything goes well ($)
5. Most Likely | Your expected/typical cost ($)
6. Pessimistic | Worst-case cost if issues arise ($)
7. Distribution | Triangular (default) or PERT
COST RISKS SHEET:
List any known risks that could impact your costs.
Probability should be 0-1 (e.g., 0.25 = 25% chance)
Impact values are additional cost if the risk occurs ($)
VENDOR INFO SHEET:
Please complete your company information
TIPS:
• Be realistic - optimistic padding will be revealed in analysis
• Optimistic should be ≤ Most Likely ≤ Pessimistic
• Include all cost items in scope
• Use consistent currency (all USD)
• List risks you're aware of - we appreciate transparency
DELETE SAMPLE DATA before submitting your proposal.