## Instructions
RFP INTEGRATED TEMPLATE - VENDOR INSTRUCTIONS
Thank you for your proposal. This template enables standardized
risk-adjusted evaluation of schedule AND cost across all vendors.
SHEETS TO COMPLETE
1. DELIVERABLES | Your project schedule with task durations
- Deliverable_ID | Unique ID (e.g., D001, D002)
- Optimistic/Most Likely/Pessimistic | Duration in DAYS
- Predecessors | Which tasks must complete first
2. COST ITEMS | Your cost breakdown with pricing
- Item_ID | Unique ID (e.g., C001, C002)
- Linked Deliverable(s) | Which tasks this cost relates to
- Cost Type | Fixed = same regardless of duration
Variable = scales if deliverable takes longer
- Optimistic/Most Likely/Pessimistic | Cost in DOLLARS
3. SCHEDULE RISKS | Known risks affecting your timeline
- Probability | 0-1 (e.g., 0.30 = 30% chance)
- Impact values | Additional DAYS if risk occurs
4. COST RISKS | Known risks affecting your pricing
- Probability | 0-1 (e.g., 0.25 = 25% chance)
- Impact values | Additional DOLLARS if risk occurs
5. VENDOR INFO | Your company details and proposal summary
KEY PRINCIPLES
✓ Be realistic | Optimistic padding is revealed by analysis
✓ Be complete | Include all deliverables and cost items in scope
✓ Be transparent | List known risks - we value honesty
✓ Be consistent | Optimistic ≤ Most Likely ≤ Pessimistic
IMPORTANT: Delete sample data before submitting.
Questions? Contact procurement at [email]

## Schedule
Task_ID | Name | Start Date | End Date | Optimistic | Most Likely | Pessimistic | Predecessors | Distribution
D001 | Requirements & Planning | 2025-04-01 | 2025-04-15 | 10 | 14 | 21 |  | Triangular
D002 | Design & Architecture | 2025-04-15 | 2025-04-30 | 12 | 15 | 22 | D001 | Triangular
D003 | Development Phase 1 | 2025-04-30 | 2025-05-30 | 25 | 30 | 42 | D002 | PERT
D004 | Development Phase 2 | 2025-05-30 | 2025-06-20 | 18 | 21 | 30 | D003 | PERT
D005 | Integration & Testing | 2025-06-20 | 2025-07-10 | 15 | 20 | 28 | D004 | Triangular
D006 | Deployment & Training | 2025-07-10 | 2025-07-20 | 8 | 10 | 15 | D005 | Triangular

## Cost Estimates
Item_ID | Name | Category | Task_ID | Cost_Type | Optimistic | Most Likely | Pessimistic | Distribution
C001 | Project Management | Labor | D001,D002,D003,D004,D005,D006 | Variable | 35000 | 45000 | 60000 | Triangular
C002 | Business Analysis | Labor | D001,D002 | Variable | 18000 | 22000 | 30000 | PERT
C003 | Solution Architecture | Labor | D002 | Variable | 20000 | 25000 | 35000 | Triangular
C004 | Development Team | Labor | D003,D004 | Variable | 95000 | 120000 | 160000 | PERT
C005 | QA & Testing | Labor | D005 | Variable | 28000 | 35000 | 48000 | Triangular
C006 | Software Licenses | Software |  | Fixed | 22000 | 28000 | 36000 | Triangular
C007 | Cloud Infrastructure | Infrastructure |  | Fixed | 18000 | 24000 | 32000 | Triangular
C008 | Training & Handover | Services | D006 | Fixed | 12000 | 15000 | 20000 | PERT

## Schedule Risks
Risk_ID | Description | Task_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
SR001 | Resource availability constraints | D003,D004 | 0.25 | 5 | 10 | 18 | Triangular | Open
SR002 | Requirements changes mid-project | D001,D002,D003 | 0.3 | 5 | 12 | 20 | PERT | Open
SR003 | Integration complexity higher than expected | D005 | 0.2 | 4 | 8 | 14 | Triangular | Open
SR004 | Vendor/third-party delays | D003,D004 | 0.15 | 5 | 10 | 20 | Triangular | Open

## Cost Risks
Risk_ID | Description | Item_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
CR001 | Scope expansion | C001,C004 | 0.35 | 15000 | 30000 | 55000 | Triangular | Open
CR002 | Additional license requirements | C006 | 0.2 | 5000 | 12000 | 22000 | Triangular | Open
CR003 | Infrastructure scaling needs | C007 | 0.25 | 8000 | 15000 | 28000 | PERT | Open
CR004 | Extended testing cycles | C005 | 0.3 | 8000 | 15000 | 25000 | Triangular | Open

## Vendor Info
VENDOR INFORMATION
Company Name: | [Enter your company name]
Contact Person: | [Enter contact name]
Email: | [Enter email]
Phone: | [Enter phone]
Date Submitted: | [Enter date]
PROPOSAL SUMMARY
Total Quoted Price: | [Enter total quoted price]
Quoted Timeline: | [Enter total weeks/months]
ASSUMPTIONS & NOTES
[Add any key assumptions about your estimates]
[Add notes about risks or dependencies]
[Add any exclusions or clarifications]