## Schedule
Task_ID | Name | Start Date | End Date | Optimistic | Most Likely | Pessimistic | Predecessors | Distribution
D001 | Requirements Document | 2025-04-01 | 2025-04-15 | 10 | 14 | 21 |  | Triangular
D002 | Design Specification | 2025-04-15 | 2025-04-30 | 12 | 15 | 22 | D001 | Triangular
D003 | Development Phase 1 | 2025-04-30 | 2025-05-30 | 25 | 30 | 42 | D002 | PERT
D004 | Testing & QA | 2025-05-30 | 2025-06-15 | 12 | 15 | 20 | D003 | Triangular
D005 | Deployment | 2025-06-15 | 2025-06-22 | 5 | 7 | 12 | D004 | Triangular

## Risks
Risk_ID | Description | Task_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
R001 | Resource availability constraints | D003 | 0.25 | 5 | 10 | 18 | Triangular | Open
R002 | Requirements changes | D001,D002 | 0.3 | 3 | 7 | 14 | Triangular | Open
R003 | Integration complexity | D004 | 0.2 | 3 | 5 | 10 | PERT | Open

## Vendor Info
VENDOR INFORMATION
Company Name: | [Enter your company name]
Contact Person: | [Enter contact name]
Email: | [Enter email]
Phone: | [Enter phone]
Date Submitted: | [Enter date]
PROPOSAL NOTES
[Add any notes or assumptions about your schedule estimates]

## Instructions
RFP SCHEDULE TEMPLATE - VENDOR INSTRUCTIONS
Thank you for your proposal. Please complete this template to help us
evaluate schedule risk across all vendors consistently.
HOW TO COMPLETE
DELIVERABLES SHEET:
1. Deliverable_ID | Unique ID for each deliverable (e.g., D001)
2. Description | Brief description of the deliverable
3. Start/End Date | Your planned dates for this deliverable
4. Optimistic | Best-case duration if everything goes well (days)
5. Most Likely | Your expected/typical duration (days)
6. Pessimistic | Worst-case duration if issues arise (days)
7. Predecessors | Which deliverables must finish first (comma-separated)
8. Distribution | Triangular (default) or PERT
SCHEDULE RISKS SHEET:
List any known risks that could impact your schedule.
Probability should be 0-1 (e.g., 0.25 = 25% chance)
Impact values are additional days if the risk occurs
VENDOR INFO SHEET:
Please complete your company information
TIPS:
• Be realistic - optimistic padding will be revealed in analysis
• Optimistic should be ≤ Most Likely ≤ Pessimistic
• Include all deliverables in scope
• List risks you're aware of - we appreciate transparency
DELETE SAMPLE DATA before submitting your proposal.