## Schedule
Task_ID | Name | Predecessors | Start Date | End Date | Optimistic | Most Likely | Pessimistic | Distribution
T1 | Project Kickoff |  | 2025-03-01 | 2025-03-06 | 3 | 5 | 8 | Triangular
T2 | Requirements Gathering | T1 | 2025-03-06 | 2025-03-21 | 10 | 15 | 25 | Triangular
T3 | Design Phase | T2 | 2025-03-21 | 2025-04-10 | 15 | 20 | 30 | PERT
T4 | Development - Module A | T3 | 2025-04-10 | 2025-05-10 | 20 | 30 | 50 | Triangular
T5 | Development - Module B | T3 | 2025-04-10 | 2025-05-15 | 25 | 35 | 55 | Triangular
T6 | Integration Testing | T4,T5 | 2025-05-15 | 2025-05-30 | 10 | 15 | 25 | PERT
T7 | User Acceptance Testing | T6 | 2025-05-30 | 2025-06-14 | 10 | 15 | 20 | Triangular
T8 | Deployment | T7 | 2025-06-14 | 2025-06-24 | 5 | 10 | 15 | Triangular

## Risks
Risk_ID | Description | Task_ID | Probability | Optimistic | Most Likely | Pessimistic | Distribution | Status
R1 | Resource availability issues | T4,T5 | 30% | 5 | 10 | 20 | Triangular | Open
R2 | Integration complexity higher than expected | T6 | 40% | 3 | 7 | 15 | PERT | Open
R3 | Scope creep during UAT | T7 | 25% | 2 | 5 | 12 | Triangular | Open
R4 | Deployment environment issues | T8 | 20% | 1 | 3 | 7 | Triangular | Open

## Instructions
SCHEDULE RISK ANALYZER - TEMPLATE INSTRUCTIONS
SCHEDULE SHEET
Task_ID | Unique identifier for each task (e.g., T1, T2, TASK-001)
Name | Task name or description
Predecessors | Task IDs that must complete before this task starts (comma-separated)
Start Date | Planned start date
End Date | Planned end/finish date
Optimistic | Best-case duration in days (if everything goes well)
Most Likely | Most likely duration in days (typical scenario)
Pessimistic | Worst-case duration in days (if things go wrong)
Distribution | Triangular (default) or PERT
RISKS SHEET (Optional)
Risk_ID | Unique identifier for each risk
Description | Description of the risk event
Task_ID | Task(s) affected by this risk (comma-separated for multiple)
Probability | Likelihood of risk occurring (0 to 1, e.g., 0.3 = 30%)
Optimistic | Minimum impact in days if risk occurs
Most Likely | Expected impact in days if risk occurs
Pessimistic | Maximum impact in days if risk occurs
Distribution | Triangular (default) or PERT
Status | Open or Closed (only Open risks are included in analysis)
TIPS
• Optimistic should be ≤ Most Likely ≤ Pessimistic
• Use PERT distribution when you want the most likely value to have more weight
• Probability should be between 0 and 1 (not percentage)
• Delete sample data and add your own before uploading